# Project Charter

Gamberini – Stained Glass Restoration Workflow System

| Field | Details |
| --- | --- |
| Project Name | Gamberini – Stained Glass Restoration Workflow System |
| Project ID | SG-RESTORE-2026-001 |
| Grantor or Customer | European Commission – Creative Europe Programme (Grant Agreement No. CE-2026-DH-0123). Parish Churches of Bologna Diocese; Superintendency of Fine Arts; Private clients; Restoration laboratory team |

| Document Version | Date | Contributor | State |
| --- | --- | --- | --- |
| 1.0 | 2026-05-15 | Kourosh “Cyrus” Shahbazi | Approved |

# 1. Project Description

The Gamberini studio is a 3rd generation laboratory that produces stained glass for churches, private chapels, decorative lamps, and glass artefacts. It also performs restoration and reparation of historical and modern stained-glass windows. Currently, the studio manages restoration requests, condition assessments, photographic documentation, material inventory, and client reporting through paper forms, spreadsheets, and informal social media groups as hub for communication, leading to lost information, scheduling conflicts, and compliance risks with EU cultural heritage funding.

This project will design and implement a lightweight digital workflow system (web‑based) to manage the entire restoration and reparation process: from initial client request, through diagnostic recording, assignment of restorers, inventory tracking of glass/lead/solders, to final quality check and reporting. The system will also generate structured reports required by the EU grant.

Domain: cultural heritage conservation (glass) + small‑enterprise process management.
Context: funded under “European Heritage Innovation” call – digitalization of traditional craftsmanship.

# 2. Project Scope

General scope: To develop and deploy a restoration workflow management system that increases traceability, reduces administrative overhead, and ensures compliance with EU reporting obligations.

Expected outcomes:

A functional web application accessible from desktop and tablet.

Reduction of manual paperwork by at least 70% for each restoration order.

Full traceability of each restored object: from initial damage log to final delivery.

EU‑compliant cost and material reports generated automatically.

Training of 5 studio operators to use the system autonomously.

Out of scope:

Production of new stained glass (new commissions).

Hardware purchase (the studio already has workstations).

Mobile native apps (responsive web only).

# 3. Deliverable List

| Code | Name | Type | Due Date |
| --- | --- | --- | --- |
| D01 | Requirements Specification (SRS) | Internal | 30/06/2026 |
| D02 | Prototype UI mockups | Internal | 20/07/2026 |
| D03 | Database schema | Internal | 10/08/2026 |
| D04 | Restoration workflow software | External | 15/10/2026 |
| D05 | User manual (for restorers) | External | 30/10/2026 |
| D06 | EU grant compliance report generator | External | 15/11/2026 |
| D07 | Test suite report | Internal | 30/11/2026 |
| D08 | Training completion certificate | External | 15/12/2026 |

# 4. Constraints

Fixed budget: total eligible costs ≤ €48,000.

Regulatory requirement to record material provenance.

Low digital literacy among users → simple UI needed.

Standalone system (no ERP integration required).

Delivery deadline: 15/12/2026.

GDPR compliance and on‑premise data storage.

# 5. Risk Analysis

| ID | Risk | Likelihood | Impact | Score | Mitigation |
| --- | --- | --- | --- | --- | --- |
| R1 | Senior restorers refuse digital system | 7 | 8 | 56 | Key user involvement |
| R2 | Underestimation of report generator effort | 6 | 7 | 42 | Develop in parallel |
| R3 | Changing EU requirements | 3 | 9 | 27 | Monthly review |
| R4 | Loss of photos (server failure) | 4 | 8 | 32 | Daily backup |
| R5 | Insufficient testing → buggy release | 5 | 8 | 40 | 15% testing allocation |

# 6. Work Breakdown Structure

| WP | Activity | Owner | Duration (days) | Effort (pd) | Dependencies |
| --- | --- | --- | --- | --- | --- |
| WP1 | Requirements gathering | PM | 10 | 6 | None |
| WP2 | UI mockups & feedback | Designer | 18 | 8 | WP1 |
| WP3 | Database design | Developer | 18 | 10 | WP1 |
| WP4 | Core coding | Developer | 50 | 25 | WP2, WP3 |
| WP5 | EU report module | Developer | 22 | 8 | WP4 |
| WP6 | Test suite execution | Tester | 60 | 12 | WP4, WP5 |
| WP7 | User manual & training | PM + Key user | 18 | 4 | WP6 |
| WP8 | Final delivery | PM | 4 | 2 | WP7 |

Critical path: WP1 → WP2 → WP4 → WP5 → WP6 → WP7 → WP8.
Total estimated effort: 75 person‑days (6 + 8 + 10 + 25 + 8 + 12 + 4 + 2)

# 7. Gantt Chart Representation

Each X represents a full day of work. Half‑days are represented with o. Critical path activities are marked with [CP].

| WBS | Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Site inspection | X |  |  |  |  |  |
| 1.2 | Draft proposal | X |  |  |  |  |  |
| 1.3 | Client approval | o |  |  |  |  |  |
| 1.4 | Order materials | o |  |  |  |  |  |
| 2.1 | Scaffolding |  | X |  |  |  |  |
| 2.2 | Remove window [CP] |  | X |  |  |  |  |
| 2.3 | Transport |  | o |  |  |  |  |
| 3.1 | Trace cartoon [CP] |  |  | o |  |  |  |
| 3.2 | Number pieces [CP] |  |  | X |  |  |  |
| 3.3 | Remove old lead [CP] |  |  | X X X |  |  |  |
| 3.4 | Assess/replace glass |  |  |  | X X |  |  |
| 3.5 | Cut new glass |  |  |  | X X |  |  |
| 3.6 | Re‑lead & solder [CP] |  |  |  | X X X X X |  |  |
| 3.7 | Cement & putty |  |  |  |  | X X |  |
| 3.8 | Clean & polish |  |  |  |  |  | X |
| 3.9 | Quality inspection |  |  |  |  |  | o |
| 4.2 | Reinstall [CP] |  |  |  |  |  | X o |

# 8. Resources (Human)

| Role | Name | Effort (pd) | Daily Cost (€) | Total (€) |
| --- | --- | --- | --- | --- |
| Project Manager | Lucia Gamberini | 12 | 350 | 4,200 |
| Developer | Marco Rossi | 43 | 300 | 12,900 |
| Tester | Elena Bianchi | 12 | 250 | 3,000 |
| UI/UX Designer | Studio Gamma | 8 | 400 | 3,200 |
| Key User | Giuseppe Verdi | 5 | 180 | 900 |

Total direct personnel & services cost: € 25.200
*Key user cost is internal (allowed as in-kind contribution, not claimed for cash).

Non-human resources:

- Laptop for testing (already owned – no additional cost).

- Local server (existing Synology NAS).

- Offline backup hard drive (1 TB) = € 70 (included in “equipment” budget).

# 9. Financial Budget

| Cost Category | Description | Estimated (€) |
| --- | --- | --- |
| Personnel costs | PM, Developer, Tester, UI designer (service), consultant | 25,200 |
| Equipment | Backup hard disk, small consumables (USB drives, printed manuals) | 300 |
| Other goods & services | Cloud backup subscription (6 months), training materials, Zoom license for remote meetings | 500 |
| Indirect costs (25%) | 25% of (A + C2 + C3) – overheads (electricity, rent, admin) | 6,500 |
| Total requested to EU | - | 32,500 |
| Co‑financing (studio 20%) | Studio own contribution | 8,125 |
| Total project value | - | 40,625 |

Since the budget is provided by EU, the requested budget by the studio is fully granted and funded.