## Gantt Chart
Gantt Chart – Gamberini Restoration Software (24 weeks, June–December 2026)
Each green block represents a full week of work ¦ [CP] = Critical Path ¦ Sprints are 2 weeks each
WBS | Activity | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12
| Week # | 1-2 | 3-4 | 5-6 | 7-8 | 9-10 | 11-12 | 13-14 | 15-16 | 17-18 | 19-20 | 21-22 | 23-24
1.1 | Req. gathering [CP] | ✦ CP
1.2 | UI mockups [CP] |  | ✦ CP | ●
1.3 | DB design |  | ●
2.1 | Core coding [CP] |  |  | ✦ CP | ✦ CP | ✦ CP | ✦ CP | ✦ CP
2.2 | EU report module | [7 empty] | ● | ●
2.3 | Test suite | [5 empty] | ● | ● | ● | ● | ● | ●
2.4 | User manual | [10 empty] | ● | ●
2.5 | Training | [11 empty] | ●
2.6 | Final delivery [CP] | [11 empty] | ✦ CP
LEGEND & PROJECT SUMMARY
✦ CP | Critical Path activity — must finish on time or project delays
● | Active sprint — work scheduled in this 2-week block
No work scheduled in this sprint
Critical Path: 1.1 Req. Gathering → 1.2 UI Mockups → 2.1 Core Coding → 2.6 Final Delivery ¦ Total Duration: 24 weeks (6 months) ¦ Total Effort: 75 person-days