## WBS
Stained Glass Window Restoration: Work Breakdown Structure | [8 empty] | Project Snapshot
6-week plan (30 working days) | [8 empty] | Total duration | 30 working days
[9 empty] | Critical path | 2.2 → 3.1 → 3.2 → 3.3 → 3.6 → 4.2
WBS | Activity Name | Owner | Duration (days) | Predecessors | Notes | Start Day | Finish Day | Phase | Milestones | Approval, studio arrival, restoration complete, handover
1.1 | Site inspection & photography | Owner | 1 |  | Assess damage, measure frame | 1 | 1 | Initiation | Key risk | Special glass delay
1.2 | Draft restoration proposal & budget | Owner | 1 | 1.1 |  | 2 | 2 | Initiation | Team | Owner, assistant, external installer
1.3 | Client approval & deposit | Owner | 0.5 | 1.2 | Milestone | 3 | 3 | Initiation
1.4 | Order special glass & materials | Assistant | 0.5 | 1.3 | Lead time risk | 3 | 3 | Initiation
2.1 | Install scaffolding / safety plan | Assistant | 0.5 | 1.3 |  | 4 | 4 | Removal
2.2 | Carefully remove window panel(s) | Owner + Asst | 1 | 2.1 | Critical path | 4 | 5 | Removal
2.3 | Pack & transport to studio | Owner | 0.5 | 2.2 |  | 5 | 5 | Removal
3.1 | Trace original window outline (cartoon) | Owner | 1 | 2.3 |  | 6 | 6 | Restoration
3.2 | Number each piece & photograph | Assistant | 1 | 3.1 |  | 7 | 7 | Restoration
3.3 | Remove old lead came & clean pieces | Assistant | 3 | 3.2 |  | 8 | 10 | Restoration
3.4 | Assess & replace broken glass | Owner | 2 | 3.3 | Wait for materials | 11 | 12 | Restoration
3.5 | Cut new glass pieces (as needed) | Owner | 2 | 3.4 |  | 13 | 14 | Restoration
3.6 | Re-lead & solder panel | Owner | 5 | 3.5 | Most time-consuming | 15 | 19 | Restoration
3.7 | Cement, putty & weatherproof | Assistant | 2 | 3.6 |  | 20 | 21 | Restoration
3.8 | Final clean & polish | Assistant | 1 | 3.7 |  | 22 | 22 | Restoration
3.9 | Quality inspection & photo documentation | Owner | 1 | 3.8 | Milestone | 23 | 23 | Restoration
4.1 | Transport window back to site | Owner | 0.5 | 3.9 |  | 24 | 24 | Reinstallation
4.2 | Reinstall window in frame | Ext. installer | 1.5 | 4.1 | Subcontracted | 25 | 26 | Reinstallation
4.3 | Repoint exterior masonry (if needed) | Ext. installer | 0.5 | 4.2 |  | 26 | 26 | Reinstallation
4.4 | Final on-site inspection & handover | Owner + client | 0.5 | 4.3 | Milestone | 26 | 26 | Reinstallation
5.1 | Prepare restoration report (before/after) | Owner | 2 | 4.4 |  | 27 | 28 | Close
5.2 | Client sign-off & final payment | Owner | 0.5 | 5.1 |  | 29 | 29 | Close
5.3 | Archive documentation & clean studio | Assistant | 1 | 5.2 |  | 30 | 30 | Close
5.4 | Post-project review (lessons learned) | Owner | 0.5 | 5.3 | Optional | 30 | 30 | Close

## Gantt
Gantt Chart — 30 Working Days
WBS | Activity | Owner | Start | Finish | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30
[5 empty] | Week 1 | Week 1 | Week 1 | Week 1 | Week 1 | Week 2 | Week 2 | Week 2 | Week 2 | Week 2 | Week 3 | Week 3 | Week 3 | Week 3 | Week 3 | Week 4 | Week 4 | Week 4 | Week 4 | Week 4 | Week 5 | Week 5 | Week 5 | Week 5 | Week 5 | Week 6 | Week 6 | Week 6 | Week 6 | Week 6
1.1 | Site inspection & photography | Owner | 1 | 1 | ■
1.2 | Draft restoration proposal & budget | Owner | 2 | 2 |  | ■
1.3 | Client approval & deposit | Owner | 3 | 3 |  |  | ■
1.4 | Order special glass & materials | Assistant | 3 | 3 |  |  | ■
2.1 | Install scaffolding / safety plan | Assistant | 4 | 4 |  |  |  | ■
2.2 | Carefully remove window panel(s) | Owner + Asst | 4 | 5 |  |  |  | ■ | ■
2.3 | Pack & transport to studio | Owner | 5 | 5 |  |  |  |  | ■
3.1 | Trace original window outline (cartoon) | Owner | 6 | 6 | [5 empty] | ■
3.2 | Number each piece & photograph | Assistant | 7 | 7 | [6 empty] | ■
3.3 | Remove old lead came & clean pieces | Assistant | 8 | 10 | [7 empty] | ■ | ■ | ■
3.4 | Assess & replace broken glass | Owner | 11 | 12 | [10 empty] | ■ | ■
3.5 | Cut new glass pieces (as needed) | Owner | 13 | 14 | [12 empty] | ■ | ■
3.6 | Re-lead & solder panel | Owner | 15 | 19 | [14 empty] | ■ | ■ | ■ | ■ | ■
3.7 | Cement, putty & weatherproof | Assistant | 20 | 21 | [19 empty] | ■ | ■
3.8 | Final clean & polish | Assistant | 22 | 22 | [21 empty] | ■
3.9 | Quality inspection & photo documentation | Owner | 23 | 23 | [22 empty] | ■
4.1 | Transport window back to site | Owner | 24 | 24 | [23 empty] | ■
4.2 | Reinstall window in frame | Ext. installer | 25 | 26 | [24 empty] | ■ | ■
4.3 | Repoint exterior masonry (if needed) | Ext. installer | 26 | 26 | [25 empty] | ■
4.4 | Final on-site inspection & handover | Owner + client | 26 | 26 | [25 empty] | ■
5.1 | Prepare restoration report (before/after) | Owner | 27 | 28 | [26 empty] | ■ | ■
5.2 | Client sign-off & final payment | Owner | 29 | 29 | [28 empty] | ■
5.3 | Archive documentation & clean studio | Assistant | 30 | 30 | [29 empty] | ■
5.4 | Post-project review (lessons learned) | Owner | 30 | 30 | [29 empty] | ■
Legend: ■ = scheduled work; highlighted rows = critical path tasks